## Trang tính1
| Project Manager: Tiêu Đăng Vinh |  |  |  |  | Project Start: | 2024-10-05
[6 empty] | Display Week: | 4 | 2024-10-26 | [6 empty] | 2024-11-02 | [6 empty] | 2024-11-09
| Task | Assign to | Check | Progress | Start day | Days | End day | 2024-10-26 | 2024-10-27 | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15
ACKNOWLEDGEMENTS
| Acknowledgements | Vinh | All | 100% | 2024-10-06 | 4 | 2024-10-09
COMMITMENTS
| Commitments | Vinh | All | 100% | 2024-10-06 | 4 | 2024-10-09
EXECUTIVE SUMMARY
| Executive Summary | Vinh | All | 100% | 2024-10-06 | 4 | 2024-10-09
TABLE OF CONTENTS
| Table of contents | Tiến | Vinh | 100% | 2024-10-07 | 3 | 2024-10-09
LIST OF FIGURES
| List of figures | Tiến | Vinh | 100% | 2024-10-07 | 3 | 2024-10-09
LIST OF TABLES
| Lists of tables | Tiến | Vinh | 100% | 2024-10-07 | 3 | 2024-10-09
LIST OF ABBREVIATIONS
| List of Abbreviations | Tiến | Vinh | 100% | 2024-10-07 | 3 | 2024-10-09
CHARTS
| Gantt chart | Tiến | Vinh | 100% | 2024-10-05 | 36 | 2024-11-09
| Pert chart | Tiến | Vinh | 100% | 2024-10-06 | 36 | 2024-11-10
Part 1 | INTRODUCTION TO THE PROJECT |  |  |  | 2024-10-12 | 9 | 2024-10-21
2024-01-01 | Introduction to the company | Tiến | Vinh | 100% | 2024-10-12 | 2 | 2024-10-13
2024-02-01 | Deliverables | Tiến | Vinh | 100% | 2024-10-12 | 2 | 2024-10-13
2024-03-01 | Overview of information system | Quỳnh Anh | Vinh | 100% | 2024-10-14 | 4 | 2024-10-17
2024-04-01 | Business problems statement | Quỳnh Anh | Vinh | 100% | 2024-10-14 | 4 | 2024-10-17
2024-05-01 | Propose solutions | Quỳnh Anh | Vinh | 100% | 2024-10-14 | 4 | 2024-10-17
2024-06-01 | Business case | Vinh | All | 100% | 2024-10-14 | 4 | 2024-10-17
2024-07-01 | Project charter | Tài | Vinh | 100% | 2024-10-18 | 4 | 2024-10-21
2024-08-01 | Assumptions | Khánh | Vinh | 100% | 2024-10-18 | 4 | 2024-10-21
2024-09-01 | System impacted | Khánh | Vinh | 100% | 2024-10-18 | 4 | 2024-10-21
2024-10-01 | Introduction to project’s methodologies | Khánh | Vinh | 100% | 2024-10-18 | 4 | 2024-10-21
Part 2 | FACT-FINDING AND REQUIREMENTS MODELING |  |  |  | 2024-10-22 | 5 | 2024-10-27
2024-01-02 | Introduction to techniques applied for Fact-finding and Requirements modeling | Tiến | Vinh | 100% | 2024-10-22 | 1 | 2024-10-22
2024-02-02 | Deliverables | Tiến | Vinh | 100% | 2024-10-22 | 1 | 2024-10-22
2024-03-02 | Current system and system architecture/diagrams (As-is business) | Quỳnh Anh | Vinh | 100% | 2024-10-23 | 5 | 2024-10-27
2024-04-02 | Business Requirement Documents | Khánh | Vinh | 100% | 2024-10-23 | 2 | 2024-10-24
2024-05-02 | Systems Requirements Documents | Tài | Vinh | 100% | 2024-10-23 | 2 | 2024-10-24
Part 3 | DATA AND PROCESS MODELING |  |  |  | 2024-10-27 | 4 | 2024-10-31
2024-01-03 | Overview and purposes | Tiến | Vinh | 100% | 2024-10-27 | 1 | 2024-10-27
2024-02-03 | Deliverables | Tiến | Vinh | 100% | 2024-10-27 | 1 | 2024-10-27
2024-03-03 | Recommended functions | Vinh | All | 100% | 2024-10-28 | 1 | 2024-10-28
2024-04-03 | Business process Modeling (BPMN) for the new system | Quỳnh Anh | Vinh | 100% | 2024-10-28 | 4 | 2024-10-31
2024-05-03 | Requirement modeling by DFD (Data Flow Diagram) | Vinh | All | 100% | 2024-10-28 | 4 | 2024-10-31
Part 4 | Object modeling |  |  |  | 2024-11-01 | 4 | 2024-11-05
2024-01-04 | Overview and purposes | Tiến | Vinh | 100% | 2024-11-01 | 1 | 2024-11-01
2024-02-04 | Deliverables | Tiến | Vinh | 100% | 2024-11-01 | 1 | 2024-11-01
2024-03-04 | Scenarios, Models and Functionality | All | All | 100% | 2024-11-02 | 3 | 2024-11-04
2024-04-04 | Class Diagram | Tài | Vinh | 100% | 2024-11-04 | 2 | 2024-11-05
2024-05-04 | Sequence diagram | Vinh | Vinh | 100% | 2024-11-04 | 2 | 2024-11-05
2024-06-04 | Activity Diagram | Quỳnh Anh | Vinh | 100% | 2024-11-04 | 2 | 2024-11-05
Part 5 | User interface design and data design |  |  |  | 2024-11-04 | 5 | 2024-11-09
2024-01-05 | User interface design | Tiến | Quỳnh Anh | 100% | 2024-11-04 | 6 | 2024-11-09
2024-02-05 | Validation | Quỳnh Anh | Khánh | 100% | 2024-11-04 | 6 | 2024-11-09
2024-03-05 | Database design | Tài | Vinh | 100% | 2024-11-04 | 6 | 2024-11-09
Part 6 | Project Plan |  |  |  | 2024-11-08 | 2 | 2024-11-09
2024-01-06 | Work Breakdown Structure | Vinh | All | 100% | 2024-11-08 | 2 | 2024-11-09
2024-02-06 | Project Milestones | Vinh | All | 100% | 2024-11-08 | 2 | 2024-11-09
Part 7 | Lessons learnt |  |  |  | 2024-11-08 | 2 | 2024-11-09
|  | All | All | 100% | 2024-11-08 | 2 | 2024-11-09